## Gp 1 - Natnl Coord Entities
Real Day/Time in ERE Event Programme | National Coordination Entitities
| NDMA/LEMA | MoH/EMTCC | Customs/Immigration | Ministry of Defence | Others (please specify or add new column)
2nd Day of Programme | 0 - 24 hrs after EQ
1630 - 2000hrs (includes debrief) | 01 Establish national response plan/mechanisms, including EOC | 01 Establish EMTCC within Health EOC | Please insert serial numbers and titles corresponding to each task in the detailed Task Sheet for this phase | Please insert serial numbers and titles corresponding to each task in the detailed Task Sheet for this phase | Please insert serial numbers and titles corresponding to each task in the detailed Task Sheet for this phase
| 02 Conduct impact assessment | 02 Conduct impact assessment | Insert | Insert | Insert
| 03 Mobilisation of national response teams | 03 Identify taskings for national EMTs | Insert | Insert | Insert
| 04 Activate international assistance, liaise with other national and international coordination entities to define priorities | 04 Recommend requests for international EMTs, liaise with WHO and moderate EMTCC space on VO | Insert | Insert | Insert
3rd Day of Programme | Day 1-2 After EQ
0900 - 1230hrs (includes debrief) | 05 Collective briefing for national responders | 05 Consolidate and expand tasking plan | Insert | Insert | Insert
| 06 Liaise over arrival arrangements of RDC | 06 Provide technical support to RDC for EMTs | Insert | Insert | Insert
| 07 Facilitate establishment of OSOCC and UCC, meet with UNDAC | 07 Process arriving international EMTs, including special entry arrangements | Insert | Insert | Insert
| 08 Screen further offers of international assistance | 08 Licensing, registration and task briefings to individual international EMTs | Insert | Insert | Insert
1330 - 1700hrs (includes debrief) | 09 Briefing to executive | 09 Coordinate operations support for EMTs | Insert | Insert | Insert
| 10 Press conference / media interviews | 10 Establish patient referral procedures, including liaison with UCC | Insert | Insert | Insert
| 11 Collate and submit reports | 11 Synthesise national EMT MDS and produce EMTCC SITREP | Insert | Insert | Insert
4th Day of Programme | Day 3-6 After EQ
0900 - 1230hrs (includes debrief) | 12 Meet with UNDAC and UCC | 12 Briefing to MoH executive | Insert | Insert | Insert
| 13 Meet with RC/HC | 13 1st collective TL meeting for EMTs | Insert | Insert | Insert
| 14 Meet with EMTCC | 14 Dealing with complaints about international EMTs, and meet with LEMA/NDMA | Insert | Insert | Insert
1330 - 1700hrs (includes debrief) | 15 Briefing to executive | 15 Site field vistis to EMTs | Insert | Insert | Insert
| 16 Attend OSOCC Meeting | 16 Attend OSOCC meeting | Insert | Insert | Insert
| 17 Collate and submit reports | 17 Synthesise all EMT MDS and produce EMTCC SITREP | Insert | Insert | Insert
| Day 7 - 10 After EQ | Day 14 After EQ | Day 7 - 10 After EQ
1800 - 2000hrs (includes debrief) | 18 Meet with UNDAC | 18 Public health outbreak and disease surveillance system | Insert | Insert | Insert
| 19 Identify additional needs | 19 2nd collective TL meeting for EMTs and retasking | Insert | Insert | Insert
| 20 Develop transition planning | 20 Press conference / media interviews | Insert | Insert | Insert
5th Day of Programme | Day 7 - 10 After EQ | Day 14 After EQ | Day 7 - 10 After EQ
0900 - 1230hrs (includes debrief) | 21 Joint press conference with UNDAC | 21 Transition planning | Insert | Insert | Insert
| 22 Facilitate demobilisation of exiting teams | 22 Manage handover and exit of T1 EMTs | Insert | Insert | Insert
| 23 Final reporting | 23 Planning deactivation of EMTCC | Insert | Insert | Insert

## Gp 2 - Natnal Response Teams
Real Day/Time in ERE Event Programme | National Response Teams
| National USAR | National EMT | Other (please specify or add new column)
2nd Day of Programme | 0 - 24 hrs after EQ
1630 - 2000hrs (includes debrief) | 01 Mobilisation of USAR personnel and deployment systems | 01 Mobilisation of EMT personnel and deployment systems | Please insert serial numbers and titles corresponding to each task in the detailed Task Sheet for this phase
| 02 Establish BoO | 02 Receive tasking from EMTCC | Insert
| 03 Conduct assessments | 03 Insertion of EMT into task location | Insert
|  | 04 Site/facility assessment and work prioritisation | Insert
3rd Day of Programme | Day 1-2 After EQ
0900 - 1230hrs (includes debrief) | 04 Work prioritisation and develop Plan of Action | 05 Deal with operations support challenges | Insert
Insert
|  | 06 Submit MDS Daily Report to EMTCC | Insert
1330 - 1700hrs (includes debrief) | 05 Deal with logistics challenges |  | Insert
| 06 Liaison with national EMT over patient transfer | 07 Apply patient referral procedures, including transfer from national USAR | Insert
| 08 Submit reporting |  | Insert
4th Day of Programme | Day 3-6 After EQ
0900 - 1230hrs (includes debrief) | 09 Continue operations | 08 Apply patient referral procedures, including transfer to international EMT | Insert
|  | 09 1st collective TL meeting for EMTs | Insert
Insert
1330 - 1700hrs (includes debrief) |  | 10 Site field vistis from EMTCC to national EMTs | Insert
| 10 Media interviews |  | Insert
| 11 Submit reporting |  | Insert
| Day 7 - 10 After EQ | Day 14 After EQ | Day 7 - 10 After EQ
1800 - 2000hrs (includes debrief) | 12 Support establishment of DACC - focus on "beyond the rubble" | 11 Public health outbreak and disease surveillance system | Insert
|  | 12 2nd collective TL meeting for EMTs | Insert
|  | 13 Media interviews | Insert
5th Day of Programme | Day 7 - 10 After EQ | Day 14 After EQ | Day 7 - 10 After EQ
0900 - 1230hrs (includes debrief) | 13 Exit planning | 14 Exit planning | Insert
| 14 Demobilisation procedures | 15 Demobilisation procedures | Insert
| 15 Preparing for post-deplotment procedures | 16 Preparing for post-deployment procedures | Insert

## Gp 3 - Intnl Coord Entities
Real Day/Time in ERE Event Programme | Internaitonal Coordination Entities
| OSOCC (or equivalent) | UCC | UN CMCoord | Other (please specify or add new column)
2nd Day of Programme | 0 - 24 hrs after EQ
1630 - 2000hrs (includes debrief) | 01 Activation of UNDAC team / regional equivalent | Not yet activated | Please insert serial numbers and titles corresponding to each task in the detailed Task Sheet for this phase | Please insert serial numbers and titles corresponding to each task in the detailed Task Sheet for this phase
| 02 Establish communications with national counterparts, activate international response teams and moderate VO | Not yet activated | Insert | Insert
| 03 Conduct internal pre-deployment procedures | Not yet activated | Insert | Insert
| 04 Draft Plan of Action | Not yet activated | Insert | Insert
3rd Day of Programme | Day 1-2 After EQ
0900 - 1230hrs (includes debrief) | 05 Arrival process through customs/immigration and take over management of RDC | Not yet activated | Insert | Insert
| 06 Establish OSOCC / regional equivalent | Not yet activated
| 07 Meetings with NDMA/LEMA and UCC | 01 Establish provisional UCC and moderate UCC space on VO
| 08 Meet with RC/HC | 02 Meetings with NDMA/LEMA and OSOCC
1330 - 1700hrs (includes debrief) | 09 Facilitate 1st OSOCC Meeting | 03 Attend 1st OSOCC Meeting | Insert | Insert
| 10 Update Plan of Action, moderate VO | 04 Expand sectorisation and tasking plan using ICMS
| 11 Meet with other stakeholders | 05 UCC meeting with sector coordinators
| 12 Collate and submit SITREP | 06 Establish patient referral procedures, including liaison with EMTCC
4th Day of Programme | Day 3-6 After EQ
0900 - 1230hrs (includes debrief) | 13 High level visit | 07 Submit UCC incident summary for USAR operations | Insert | Insert
| 14 Private sector coordination | 08 UCC meeting with sector coordinators | Insert | Insert
| 15 Discuss cash based programming |  | Insert | Insert
1330 - 1700hrs (includes debrief) | 16 Support prioritisation for Flash Appeal | 09 Logistics request for heavy lifting capacity | Insert | Insert
| 17 Facilitate 2nd OSOCC Meeting | 10 Attend 2nd OSOCC Meeting | Insert | Insert
| 18 Update call with OCHA HQ | 11 Press conference / media interviews | Insert | Insert
Day 7 - 10 After EQ
1800 - 2000hrs (includes debrief) | 19 Meeting with NDMA/LEMA | 12 Support government in establishing DACC - focus on "beyond the rubble" | Insert | Insert
| 20 Identify additional needs |  | Insert | Insert
| 20 Develop a handover/transition plan |  | Insert | Insert
5th Day of Programme | Day 7 - 10 After EQ
0900 - 1230hrs (includes debrief) | 21 Joint press conference with NDMA/LEMA | 13 Develop collated demobilsation plan | Insert | Insert
| 22 High level visit | 14 Deal with incoming USAR team after official announcement "USAR phase over" | Insert | Insert
| 23 Submit handover report | 15 Submit incident summary for USAR operations | Insert | Insert

## Gp 4 - Intnl Response Teams
Real Day/Time in ERE Event Programme | International Response Teams
| International USAR | International EMT | Other (please specify or add new column)
2nd Day of Programme | 0 - 24 hrs after EQ
1630 - 2000hrs (includes debrief) | 01 Monitor in-country situation on VO | 01 Monitor in-country situation on VO | Please insert serial numbers and titles corresponding to each task in the detailed Task Sheet for this phase
| 02 Activate team standby and pre-deployment procedures | 02 Activate team standby and pre-deployment procedures | Insert
| 03 Liaise with national and international coordination entities | 03 Liaise with WHO and MoH over possible taskings | Insert
| 04 Prepare offer of assistance and registration documentation | 04 Prepare offer of assistance and registration documentation | Insert
3rd Day of Programme | Day 1-2 After EQ
0900 - 1230hrs (includes debrief) | 05 Arrival process through customs/immigration and liaise with national authorities to establish and manage RDC | 05 Arrival process through customs/immigration and RDC | Insert
| 06 Hand over RDC management to incoming UNDAC team | 06 Licensing, registration and task briefings to individual international EMTs | Insert
| 07 Support establishment of UCC | 07 Deal with operations support challenges | Insert
1330 - 1700hrs (includes debrief) | 08 Establish BoO | 08 Site/facility assessment and work prioritisation | Insert
| 09 UCC briefing with sector coordinators, to include discussion with EMTs over procedures for patient transfer | 09 Apply patient referral procedures, including transfer from national USAR | Insert
Insert
4th Day of Programme | Day 3-6 After EQ
0900 - 1230hrs (includes debrief) | 11 Sector coordinators to brief teams | 10 Apply patient referral procedures, including liaison with national EMTs | Insert
| 12 Teams further develop Plan of Action | 11 1st collective TL meeting for EMTs | Insert
| 13 Teams conduct assessments according to tasking, liaison with international EMTs over procedures for patient transfer | 12 Submit MDS Daily Report to EMTCC, and liaison with international USAR over patient transfer | Insert
1330 - 1700hrs (includes debrief) | 14 Teams report on assessments | 13 Site field vistis from EMTCC to international EMTs | Insert
| 15 OSOCC meeting |  | Insert
| 16 Sector coordinators develop and submit sector summaries, and media interviews |  | Insert
| Day 7 - 10 After EQ | Day 14 After EQ | Day 7 - 10 After EQ
1800 - 2000hrs (includes debrief) | 17 Support government in establishing DACC - focus on "beyond the rubble" | 14 Public health outbreak and disease surveillance system | Insert
|  | 15 2nd collective TL meeting for EMTs | Insert
|  | 16 Media interviews | Insert
5th Day of Programme | Day 7 - 10 After EQ | Day 14 After EQ | Day 7 - 10 After EQ
0900 - 1230hrs (includes debrief) | 18 Exit planning | 17 Exit planning | Insert
| 19 Demobilisation procedures | 18 Demobilisation procedures | Insert
| 20 Post-deployment procedures | 19 Post-deployment procedures | Insert

## Gp 5 - Humantn Coord Partners
Real Day/Time in ERE Event Programme | Humanitarian Coordination Partners
| HCT | Clusters (specify or add new column) | Other (please specify or add new column)
2nd Day of Programme | 0 - 24 hrs after EQ
1630 - 2000hrs (includes debrief) | Please insert serial numbers and titles corresponding to each task in the detailed Task Sheet for this phase | Please insert serial numbers and titles corresponding to each task in the detailed Task Sheet for this phase | Please insert serial numbers and titles corresponding to each task in the detailed Task Sheet for this phase
| Insert | Insert | Insert
| Insert | Insert | Insert
| Insert | Insert | Insert
3rd Day of Programme | Day 1-2 After EQ
0900 - 1230hrs (includes debrief) | Insert | Insert | Insert
| Insert | Insert | Insert
| Insert | Insert | Insert
1330 - 1700hrs (includes debrief) | Insert | Insert | Insert
| Insert | Insert | Insert
| Insert | Insert | Insert
4th Day of Programme | Day 3-6 After EQ
0900 - 1230hrs (includes debrief) | Insert | Insert | Insert
| Insert | Insert | Insert
| Insert | Insert | Insert
1330 - 1700hrs (includes debrief) | Insert | Insert | Insert
| Insert | Insert | Insert
| Insert | Insert | Insert
Day 7 - 10 After EQ
1800 - 2000hrs (includes debrief) | Insert | Insert | Insert
| Insert | Insert | Insert
| Insert | Insert | Insert
5th Day of Programme | Day 7 - 10 After EQ
0900 - 1230hrs (includes debrief) | Insert | Insert | Insert
| Insert | Insert | Insert
| Insert | Insert | Insert